## Sheet1
2021-04-29 | TO-DO 6/05/2021 | Done 6/05/2021 | TO-DO 13/05/2021 | Done 13/05/2021 | TO-DO 20/05/2021 | Done 20/05/2021 | TO-DO 27/05/2021 | Done 27/05/2021 | TO-DO 3/06/2021 | Done 3/06/2021 | TO-DO Final 7/06/2021
Basic Framework | Engine werkend krijgen | Engine werkend krijgen | Update tijd FPS counter aanpassen 1 slot | Update tijd FPS counter aanpassen | Art-work Q*bert 2 slots | Art-work Q*bert | Game-board Implementeren 4 slots | Game-board reader | Game-Board Implementatie afwerken 1 slot
| Enkele components toevoegen | Enkele components toevoegen | Command pattern 2 slots | Basic command pattern | Game-board Implementeren 5 slots |  | Q*bert player char 2 slots |  | Q*bert player char 2 slots
| Basic scene in de game steken | Basic scene in de game steken | Project met Engine subproject en Game subproject 2 slots | Project met Engine subproject en Game subproject | Q*bert player char 2 slots |  | Teleportation disks 2 slots |  | Teleportation disks 2 slots
| FPS counter | FPS counter | Art-work Q*bert 2 slots |  | Optioneel: Teleportation disks |  | Coily enemy char 4 slots |  | Coily enemy char 4 slots
|  | Alles van pointers naar smart_pointers | Game-board Implementeren 5 slots |  |  |  | Point system 2 slots |  | Point system 2 slots
|  |  | Q*bert player char 2 slots | [5 empty] | UI 2 slots